{"text_format":"2","workbook":"xlsx","n_sheets":1,"sheets":["Sheet1"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Sheet1","index":0,"n_rows":284,"n_cols":18,"rows_kept":284,"cut":false,"hidden":false,"merged":[]}
["序号","项目名称","建设性质","建设起止年限","总投资","2021年前已累计完成纳统投资","2022年计划纳统投资","2022年实际完成投资","12月实际纳统投资","2022年剩余纳统投资","是否民间投资项目（填是否）","是否产业投资项目（填是否）","行业分类","是否入库","是否开工","责任单位","存在问题","备注"]
[1,"滇红国际购物中心","续建",null,40000,40000,0,0,0,0,"是","否","房地产","是","是","县住建局",null,"投资已报完"]
[2,"凤庆县鲁史镇永新片区旧区综合改造项目","续建",null,8000,8000,0,0,0,0,"是","否","房地产","是","是","县住建局",null,"投资已报完"]
[3,"凤庆县秀水庭院建设项目","续建",null,8000,8000,0,0,0,0,"是","否","房地产","是","是","县住建局",null,"投资已报完"]
[4,"滇红国际","续建",null,60000,60000,0,0,0,0,"是","否","房地产","是","是","县住建局",null,"投资已报完"]
[5,"幸福锦城","续建",null,20000,20000,0,0,0,0,"是","否","房地产","是","是","县住建局",null,"投资已报完"]
[6,"凤庆滇红盛园建设项目","续建",null,20000,20000,0,0,0,0,"是","否","房地产","是","是","县住建局",null,"投资已报完"]
[7,"凤庆县城北部农贸市场建设项目","续建",null,7300,7300,0,0,0,0,"是","否","房地产","是","是","县住建局",null,"投资已报完"]
[8,"凤凰城建设项目","续建",null,25000,25000,0,0,0,0,"是","否","房地产","是","是","县住建局",null,"投资已报完"]
[9,"凤庆县山水郡建设项目","续建",null,4000,4000,0,0,0,0,"是","否","房地产","是","是","县住建局",null,"投资已报完"]
[10,"凤庆县“雪山·锦苑”","续建",null,7000,7000,0,0,0,0,"是","否","房地产","是","是","县住建局",null,"投资已报完"]
[11,"雪山综合交易市场建设项目","续建",null,12000,12000,0,0,0,0,"是","否","房地产","是","是","县住建局",null,"投资已报完"]
[12,"凤庆县运输公司片区综合开发建设项目","续建","2020-2022",15595,15340,1000,255,0,0,"否","是","其他","是","是","县住建局","投资已基本报完","投资已基本报完"]
[13,"凤庆县污水处理提质增效项目","续建","2020-2022",17000,16980,20,0,0,20,"否","是","能源以外工业","是","是","县住建局","投资已基本报完","投资已基本报完"]
[14,"凤庆县北部商贸城建设项目","续建","2020-2021",13500,13493,7,0,0,7,"是","是","其他","是","是","县住建局","投资已基本报完","投资已基本报完"]
[15,"凤庆县城西环路禾家庄至凤一中段（含保平路）","续建","2017-2020",94894,38591,8000,29114,996,28185,"否","否","综合交通","是","是","县住建局","无","无"]
[16,"2021年凤庆县公建办公楼智慧幕墙及系统控制建设项目","续建","2021-2022",5970,3000,3000,2970,0,0,"否","是","数字经济","是","是","县住建局","投资已报完","投资已报完"]
[17,"凤庆滇红生态产业园区冷链物流仓储暨托管交易中心建设项目","续建","2021-2022",35000,22155,11800,14050,0,-1205,"否","否","其他","是","是","园区管委会","投资已报完","投资已报完"]
[18,"凤庆县乡村振兴“一县一业”核桃基配油生产加工建设项目","续建","2020-2022",19198.45,13320,1400,5878,0,0.450000000000728,"否","是","能源以外工业","是","是","园区管委会","投资已报完","投资已报完"]
[19,"凤庆陈升红茶业有限责任公司总部基地","续建","2020-2023",20000,6670,1340,9155,800,4975,"是","是","能源以外工业","是","是","园区管委会","项目推进缓慢","项目推进缓慢"]
[20,"凤庆禅茶文化庄园（二期）建设项目","续建","2021-2022",14000,10200,3000,3800,0,0,"是","是","文化旅游","是","是","园区管委会","投资已报完","投资已报完"]
[21,"凤庆县扁乌线（扁口至尖石段）县乡道改造工程一期工程","续建","2017-2020",24685,130,2000,0,0,24555,"否","否","综合交通","是","是","县交运局","停工，无施工单位，无法支撑投资","停工，无施工单位，无法支撑投资"]
[22,"云县至雅琅河县乡道改造工程凤庆段","续建","2017-2020",13814,5879,2000,0,0,7935,"否","否","综合交通","是","是","县交运局","停工，无施工单位，无法支撑投资","停工，无施工单位，无法支撑投资"]
[23,"凤庆县犀牛大桥","续建","2018-2020",22820,14130,3000,9766,0,-1076,"否","否","综合交通","是","是","县交运局","投资已报完","投资已报完"]
[24,"凤庆县干塘至秀塘农村公路改造项目","续建","2019-2020",6379,732,3000,5647,534,534,"否","否","综合交通","是","是","县交运局","项目推进缓慢","项目推进缓慢"]
[25,"凤庆县2020年第一批安全生命防护工程","续建","2020-2021",5567,3328,2200,1789,0,450,"否","否","综合交通","是","是","县交运局","停工","停工"]
[26,"凤庆通用机场建设项目","续建","2017-2021",79021,46208,1000,15815,3030,20028,"否","否","综合交通","是","是","县交运局","一是项目建设用地涉及生态红线问题，农用地转为建设用地未取得批复，目前，项目主体工程处于停工状态；二是场外配套工程均无上级项目支撑，地方政府资金筹措压力大。","项目推进缓慢"]
[27,"凤庆县城东环路建设项目（一期）","续建","2020-2022",45288,10053,1000,2003,0,33232,"否","否","综合交通","是","是","县交运局","一是东环路征用地160亩未完成报批，报批需缴纳被征地农民基本养老保障金479.9835万元，需补充耕地指标7.48公顷。二是还尚未找到新的合作方，还需继续寻找洽谈，新的合作方接盘前支付部分工程款给原施工方（中国水利水电第十四工程局有限公司）。","停工，无施工单位，无法支撑投资"]
[28,"凤庆中心城区供水工程","续建","2017-2021",58721,50256,5000,6400,0,2065,"否","否","水利","是","是","县水务局","因财政困难，项目资金不能及时拨付到位，现已完成投资约1350万元左右，完成支付工程进度款457万元，占总投资的19%，占已完成工程进度的33.8%，现在由于钢材原材料涨价，施工单位垫付资金压力严重，项目进展缓慢。","项目推进缓慢"]
[29,"凤庆县鹿马箐水库工程","续建","2017-2020",28511,19879,6000,911,0,7721,"否","否","水利","是","是","县水务局","省级补助资金剩余4706.494万元未到位，项目资金不足。","项目推进缓慢（投资超报）"]
[30,"凤庆县前峰水库工程","续建","2018-2020",12785,11760,1000,0,0,1025,"否","否","水利","是","是","县水务局","一是在2016年11月省烟草公司的评审过程中，由于控制总投资的原因，取消了溢洪道、进场路，核减了征地补偿费等，在初步设计初稿概算投资中核减了6186.77万元，我县投资配套压力较大。二是前锋水库重大设计变更较多，水保单项重大设计变更已经报批，现正在修改批复阶段。","停工，无施工单位，无法支撑投资"]
[31,"凤庆县涌金水库","续建","2020-2023",14329,8617,5000,467,0,5245,"否","否","水利","是","是","县水务局","一是由于项目资金不落实，影响项目推进。工程批复概算总投资为14272.42万元，按照原政策其中省级补助资金7136.21万元，其余为市县自筹解决，由于地质灾害导致增加进场路边坡处理工程及相关设计变更等原因增加投资2355.08万元也需要市县自筹，由于政策变化，省级补助资金尚未落实，目前仅到位市县自筹资金210.43万元用于前期及征地补偿。根据与省水投对接情况看，由于政策调整，近期获得省补助资金的可能性不大。二是水库淹没区涉及10.59亩基本农田尚未调出，无法办理用地征转。","停工，（投资超报）无法支撑投资"]
[32,"云南省临沧市凤庆县大摆田水库工程","续建","2020-2025",56951,21467,3470,15423,1002,21063,"否","否","水利","是","是","县水务局","一是项目区涉及1宗探矿权及1宗采矿权，经多次协商尚未达成压覆协议。其中所涉探矿权已经完成了补偿价值评估，但因资金到位不足，未能签订压覆协议。二是项目实施地方配套资金压力大，项目初设批复总投资5.79亿元中，市县需要配套资金1.81亿元,地方配套资金压力大。三是项目因涉及未批先占使用土地，为避免新增违法用地面积，相关工作面已经暂停施工，管理所正在组织用地征转报批工作，目前项目用地勘测下界已经完成验收备案，但根据省自然资源厅有关文件要求，4月15日开始启用三调数据，用地征转报批地类将以三调数据为基础开展工作，需要在相关细则明确后才能继续开展用地报批工作。","项目推进缓慢（土建施工已报完）"]
[33,"临沧市凤庆县农村供水保障专项行动项目","续建","2021-2022",16247,2075,10000,11069,1112,4215,"否","否","水利","是","是","县水务局","一是项目前期推进资金缺乏。二是实施方案已评审，但未批复，因评审费用资金未支付，评审单位不予批复。","项目推进缓慢"]
[34,"凤庆县第二人民医院二期建设项目","续建","2020-2021",22106,14410,7800,5190,870,3376,"否","否","卫生健康","是","是","县卫健局","资金筹集压力大，设备部分暂无法完成支付，造成设备投资部分无法入统。","开具发票困难，无法支撑投资"]
[35,"凤庆县第二人民医院传染楼建设项目","续建","2021-2022",5753,1130,3000,1970,130,2783,"否","否","卫生健康","是","是","县卫健局","无上级项目资金支持，建设资金缺口大。","开具发票困难，无法支撑投资"]
[36,"凤庆县小湾农牧光伏发电项目","续建","2021-2022",24600,15073,9500,9527,0,0,"是","是","能源","是","是","县发改局","无","无"]
[37,"凤庆县2021年高标准农田建设项目","续建","2021-2022",5530,2484,3500,3046,0,0,"否","是","农业","是","是","县农业农村局","投资已报完","投资已报完"]
[38,"凤庆县杨柳河肉牛养殖场建设项目","续建","2021-2022",17000,2350,14400,14650,0,0,"否","是","农业","是","是","县农业农村局","投资已报完","投资已报完"]
[39,"凤庆县滇红第一村旅游基础设施建设项目","续建","2021-2022",17820,3472,14900,14348,0,0,"否","否","文化旅游","是","是","县文旅局","投资已报完","投资已报完"]
[40,"凤庆县小湾镇鸿达综合农贸市场","续建","2020-2021",8000,7700,500,300,0,0,"是","否","房地产","是","是","小湾镇","投资已报完","投资已报完"]
[41,"凤庆县垃圾填埋场渗滤液处理站提升改造工程","续建",2021,805,750,55,55,0,0,"否","否","其他","是","是","县住建局","投资已报完","投资已报完"]
[42,"凤庆县圣喻亭书院广场建设项目","续建","2021-2022",4960,3500,1500,1450,0,10,"否","否","其他","是","是","县住建局","无","投资已基本报完"]
[43,"凤庆县2018年第一批直过民族自然村硬化路","续建","2018-2019",1721,779,200,942,0,0,"否","否","综合交通","是","是","县交运局","投资已报完","投资已报完"]
[44,"凤庆县二零一九年农村公路提级工程","续建","2019-2020",600,314,200,0,0,286,"否","否","综合交通","是","是","县交运局","财务支出法，因资金问题未报完","停工，财务支出法，无法支撑投资"]
[45,"凤庆县二零一九年通畅示范公路建设项目","续建","2019-2020",550,57,300,0,0,493,"否","否","综合交通","是","是","县交运局","财务支出法，因资金问题未报完","停工，财务支出法，无法支撑投资"]
[46,"凤庆县2020年省级资金补助交通安全工程","续建",2020,900,596,300,204,0,100,"否","否","综合交通","是","是","县交运局","计划项目，因资金问题处于停工","停工"]
[47,"凤庆县城周边旅游公路基础设施完善工程","续建","2021-2022",776,467,309,309,0,0,"否","否","综合交通","是","是","县交运局","投资已报完","投资已报完"]
[48,"凤庆县郭大寨水库中型灌区","续建",2020,2390,2078,200,312,312,312,"否","否","水利","是","是","县水务局","资金未能有效拨付，工程未完工","停工"]
[49,"凤庆县全面健康信息平台建设项目","续建","2019-2020",1632,732,900,718,46,228,"否","否","卫生健康","是","是","县卫健局","无项目资金支持","计划年底报完出库"]
[50,"凤庆县人民医院信息化升级项目","续建",2020,785,549,200,236,0,0,"否","否","卫生健康","是","是","县卫健局","投资已报完","投资已报完"]
[51,"临沧市凤庆县营盘镇秀塘村忙瓦土地整治（提质改造）项目","续建","2021-2022",2307,1950,300,357,0,0,"否","是","农业","是","是","县自然资源局","投资已报完","投资已报完"]
[52,"临沧市凤庆县第二中学建设项目","续建","2018-2020",3130,1958,800,120,40,1092,"否","否","教育体育","是","是","县教体局","因财政困难，项目资金不能及时拨付到位，项目进展缓慢。","项目进展缓慢"]
[53,"凤庆县洛党镇义务教育薄弱环节改善与能力提升校舍建设项目","续建","2021-2022",700,400,300,300,0,0,"否","否","教育体育","是","是","县教体局","投资已报完","投资已报完"]
[54,"凤庆县大寺乡义务教育薄弱环节改善与能力提升校舍建设项目","续建","2021-2022",1000,400,600,600,0,0,"否","否","教育体育","是","是","县教体局","投资已报完","投资已报完"]
[55,"凤庆乡村旅游示范村基础设施（一期）建设项目","续建","2021-2022",3562,2113,1500,1449,0,0,"否","否","文化旅游","是","是","县文旅局","投资已报完","投资已报完"]
[56,"2021年第一批上海市对口帮扶云南省凤山镇滇红第一村高原三地建设项目","续建","2021-2022",1175,390,600,785,0,0,"否","是","文化旅游","是","是","凤山镇","投资已报完","投资已报完"]
[57,"凤山镇京竹林村乡村振兴示范点建设项目","续建","2021-2022",1197,482,400,715,0,0,"否","是","文化旅游","是","是","凤山镇","投资已报完","投资已报完"]
[58,"云县地震台部分迁建综合观测站建设项目","续建","2018-2019",1780,913,900,867,0,0,"否","是","其他","是","是","洛党镇","投资已报完","投资已报完"]
[59,"凤庆县洛党镇箐头村箐头自然村宜居宜游型村庄建设项目","续建","2021-2022",3436,1500,1900,1936,0,0,"否","否","文化旅游","是","是","洛党镇","投资已报完","投资已报完"]
[60,"凤庆县洛党镇洛党村前后营自然村乡村振兴示范点建设项目","续建","2021-2022",2798,1500,1300,1298,0,0,"否","否","其他","是","是","洛党镇","投资已报完","投资已报完"]
[61,"凤庆县小湾水电站移民安置区洛党镇大兴移民安置点兴发自然村美丽家园·移民新村建设项目","续建","2021-2022",3460,600,2900,2860,0,0,"否","否","其他","是","是","洛党镇","投资已报完","投资已报完"]
[62,"凤庆县鲁史茶马古文化景区建设项目","续建","2019-2020",609,120,500,0,0,489,"否","否","文化旅游","是","是","鲁史镇","因财政困难，项目资金不能及时拨付到位，项目进展缓慢。","财务支出法，无项目资金，无法支撑投资"]
[63,"凤庆县鲁史镇生物质燃料加工厂建设项目","续建","2021-2022",1200,500," ",700,0,0,"是","是","能源","是","是","鲁史镇","投资已报完","投资已报完"]
[64,"万众缘生态牛一号养殖基地","续建",2021,1130,1086,44,44,0,0,"是","是","农业","是","是","营盘镇","投资已报完","投资已报完"]
[65,"凤庆县营盘镇云上开物食品综合加工厂建设项目","续建","2021-2022",803,748,55,55,0,0,"是","是","能源以外工业","是","是","营盘镇","投资已报完","投资已报完"]
[66,"临沧云坊农产品加工厂建设项目","续建","2021-2022",2007,42,2000,1965,0,0,"是","是","能源以外工业","是","是","营盘镇","投资已报完","投资已报完"]
[67,"凤庆县雪山镇西山片区农村污水处理项目","续建","2021-2022",798,638,160,160,0,0,"否","是","能源以外工业","是","是","雪山镇","投资已报完","投资已报完"]
[68,"凤庆县小湾镇“锦秀茶尊”旅游基础设施建设项目","续建","2021-2022",750,300,800,450,0,0,"否","否","文化旅游","是","是","小湾镇","投资已报完","投资已报完"]
[69,"凤庆县小湾镇自然村活动场所基础设施建设项目","续建","2021-2022",1800,350,1800,1450,0,0,"否","否","其他","是","是","小湾镇","投资已报完","投资已报完"]
[70,"临沧市凤庆县诗礼特困人员供养服务设施建设项目","续建","2019-2020",686,276,400,0,0,410,"否","否","其他","是","是","诗礼乡","因财政困难，项目资金不能及时拨付到位，项目进展缓慢。","因财政困难，项目资金不能及时拨付到位，项目进展缓慢。"]
[71,"大寺乡教育薄改建设项目","续建","2018-2019",622,409,133,0,0,213,"否","否","教育体育","是","是","大寺乡","因财政支出法需开具发票","因财政支出法需开具发票"]
[72,"凤庆县大寺乡2021年核桃采后处理水洗果一级加工站建设项目","续建",2020,1980,1100,600,880,0,0,"是","是","农业","是","是","大寺乡","投资已报完","投资已报完"]
[73,"郭大寨乡中心幼儿园建设项目","续建","2019-2020",622,301,0,76,0,245,"否","否","教育体育","是","是","郭大寨乡","无","无"]
[1,"凤屿湖山项目","3月新建","2022-2023",40000,0,12000,19168,418,21250,"是","否","房地产","是","是","县住建局","无","无"]
[2,"云天国际项目","3月新建",2022,7300,0,7300,7300,0,0,"是","否","房地产","是","是","县住建局","投资已报完","投资已报完"]
[3,"凤庆县腰街彝族乡通三级公路工程建设项目","3月新建","2022-2023",31118.58,0,20000,12035,1932,21015.58,"否","否","综合交通","是","是","县交运局","一是中央车购税对乡镇通三级公路补助标准为200万/公里，省级对农村公路的补助政策尚未最终确定，三级路资金缺口约250万元/公里；二是在开展三级路项目前期工作中，由于受土地、林地、生态红线、基本农田、自然保护区、饮用水源地等刚性约束影响，前置报件多、审批时限长、难度大，调规极其困难，大部分路段只能在原有道路进行改建，项目建设难以按照设计标准实施。三是项目建设资金拨付率极低，项目建设推进缓慢。","项目推进缓慢"]
[4,"凤庆县核桃全产业链智能物流园基础设施数智化建设项目","3月新建",2022,20192,0,20192,12005,0,8187,"否","是","数字经济","是","是","县发改局","无","无"]
[5,"临沧市凤庆县犀牛片区农村产业融合发展示范园建设项目","2月新建",2022,5000,0,5000,5000,0,0,"否","是","文化旅游","是","是","鲁史镇 ","投资已报完","投资已报完"]
[6,"凤庆县勐佑镇云上花海建设项目","3月新建",2022,6800,0,6800,6800,0,0,"是","是","文化旅游","是","是","勐佑镇","投资已报完","投资已报完"]
[7,"凤庆禅茶文化庄园产业融合建设项目","4月新建","2021-2023",20928,0,10000,18003,1960,4885,"是","是","文化旅游","是","是","园区管委会","项目正在有序推进","项目正在有序推进"]
[8,"凤庆河凤山-大兴段治理工程","5月新建","2022-2024",6441,0,2400,2323,0,4118,"否","否","水利","是","是","县水务局","2022年度（临财农发﹝2021﹞111号）下达的两条河道治理专项资金总额2236万元占比项目投资60%，需地方配套40%，且要求征地拆迁费用由地方自筹，相关设计、质量检测及监理服务费也尚未落实。","资金不到位（分年度下达资金），当年资金已完成，无法支撑今年投资"]
[9,"云南凤庆户用光伏建设项目","6月新建","2021-2023",79482,0,40000,9928,1502,71056,"是","是","能源","是","是","县发改局","项目进展缓慢","项目进展缓慢"]
[10,"凤庆县污水管网工程空白区新建污水管网项目","6月新建","2022-2035",17965,0,3600,13062,1012,5915,"否","否","其他","是","是","县住建局","无","无"]
[11,"凤庆县凤山镇安石村滇红茶生产示范基地建设项目","6月新建","2022-2023",8000,0,6000,8000,0,0,"否","是","能源以外工业","是","是","县文旅局","无","无"]
[12,"凤庆县城市多功能停车场（凤习路口停车场）建设项目","3月新建",2022,2600,0,2600,2623,0,-23,"否","否","综合交通","是","是","县住建局","无","无"]
[13,"凤庆县城市多功能停车场（凤山镇粮管所停车场）建设项目","3月新建",2022,2500,0,2500,2500,0,0,"否","否","综合交通","是","是","县住建局","无","无"]
[14,"凤庆县城市多功能停车场（凤庆县第一人民医院停车场）建设项目","3月新建",2022,2600,0,2600,2600,0,0,"否","否","综合交通","是","是","县住建局","无","无"]
[15,"凤庆县城市多功能停车场建设项目","3月新建",2022,1468,0,1468,1468,0,0,"否","否","综合交通","是","是","县住建局","投资已报完","投资已报完"]
[16,"凤庆县2021年自然村通硬化路建设项目","2月新建",2022,1446,0,1446,1446,0,0,"否","否","综合交通","是","是","县交运局","投资已报完","投资已报完"]
[17,"凤庆县2021年农村公路提级工程","3月新建",2022,726,0,726,726,0,0,"否","否","综合交通","是","是","县交运局","投资已报完","投资已报完"]
[18,"凤庆县乡村振兴示范点建设项目","2月新建",2022,670,0,670,670,0,0,"否","否","水利","是","是","县水务局","投资已报完","投资已报完"]
[19,"凤山镇东山村村组道路硬化项目","2月新建",2022,750,0,750,750,0,0,"否","否","综合交通","是","是","凤山镇 ","投资已报完","投资已报完"]
[20,"凤山镇乡村道路基础设施建设项目","2月新建",2022,700,0,700,700,0,0,"否","否","综合交通","是","是","凤山镇 ","投资已报完","投资已报完"]
[21,"凤庆县香寄茶业加工厂建设项目","2月新建",2022,1285,0,1285,1285,0,0,"是","是","能源以外工业","是","是","凤山镇 ","投资已报完","投资已报完"]
[22,"凤山镇京竹林村二道河撒马场乡村旅游基础设施建设项目","3月新建",2022,800,0,800,800,0,0,"否","是","文化旅游","是","是","凤山镇 ","投资已报完","投资已报完"]
[23,"凤庆县二道河茶叶加工车间建设项目","3月新建",2022,1300,0,1300,1300,0,0,"是","是","能源以外工业","是","是","凤山镇 ","投资已报完","投资已报完"]
[24,"凤庆县联建茶叶加工厂建设项目","2月新建",2022,1500,0,1500,1500,0,0,"是","是","能源以外工业","是","是","凤山镇 ","投资已报完","投资已报完"]
[25,"凤庆县小湾水电站移民安置区洛党镇大兴移民安置点兴旺自然村美丽家园.移民新村建设项目","3月新建",2022,2378,0,2378,2378,0,0,"否","是","文化旅游","是","是","洛党镇","投资已报完","投资已报完"]
[26,"洛党镇大兴村为民服务中心建设项目","3月新建",2022,817,0,817,817,0,0,"否","否","其他","是","是","洛党镇","投资已报完","投资已报完"]
[27,"凤庆县金三生猪养殖场建设项目","2月新建",2022,1250,0,1250,1250,0,0,"是","是","农业","是","是","鲁史镇","投资已报完","投资已报完"]
[28,"凤庆县营盘镇村组道路硬化建设项目","3月新建",2022,1154,0,1154,1154,0,0,"否","否","综合交通","是","是","营盘镇","投资已报完","投资已报完"]
[29,"凤庆县营盘镇2022年烤烟、甘蔗产业基础设施建设项目","3月新建",2022,2208,0,2208,2208,0,0,"否","否","其他","是","是","营盘镇","投资已报完","投资已报完"]
[30,"凤庆县营盘镇京立安温泉开发建设项目","3月新建",2022,906,0,906,906,0,0,"是","是","文化旅游","是","是","营盘镇","投资已报完","投资已报完"]
[31,"营盘镇乡村振兴示范点村组道路及入户道路硬化建设项目","3月新建",2022,2003,0,2003,2003,0,0,"否","否","综合交通","是","是","营盘镇","投资已报完","投资已报完"]
[32,"凤庆县营盘镇无害化卫生厕所及污水收集处理建设项目","3月新建",2022,1830,0,1830,1830,0,0,"否","否","其他","是","是","营盘镇","投资已报完","投资已报完"]
[33,"凤庆县营盘镇集镇基础设施建设项目","3月新建",2022,3586,0,3586,3586,0,0,"否","否","其他","是","是","营盘镇","投资已报完","投资已报完"]
[34,"凤庆县小湾镇锦秀村箐头上自然村、字家自然村、下甲山自然村，温泉村箐门口自然村、箐口自然村通硬化路建设","3月新建",2022,1050,0,1050,1050,0,0,"否","否","综合交通","是","是","小湾镇","投资已报完","投资已报完"]
[35,"凤庆县泓溢机动车检验检测站建设项目","3月新建",2022,550,0,550,550,0,0,"是","是","其他","是","是","小湾镇","投资已报完","投资已报完"]
[36,"小湾镇2021年高标准农田建设项目","3月新建",2022,2760,0,2760,2760,0,0,"否","是","农业","是","是","小湾镇","投资已报完","投资已报完"]
[37,"凤庆县三岔河镇大龙潭村畜牧养殖场建设项目","2月新建",2022,1099,0,1099,1099,0,0,"是","是","农业","是","是","三岔河镇 ","投资已报完","投资已报完"]
[38,"凤庆县三岔河镇永丰片区基础设施建设项目","3月新建",2022,2735,0,2735,2735,0,0,"否","否","其他","是","是","三岔河镇 ","投资已报完","投资已报完"]
[39,"凤庆县三岔河镇茶叶加工厂建设项目","3月新建",2022,2201,0,2201,2201,0,0,"是","是","能源以外工业","是","是","三岔河镇 ","投资已报完","投资已报完"]
[40,"凤庆县三岔河镇秀衣庄村罗家寨片区道路硬化建设项目","2月新建",2022,720,0,720,720,0,0,"否","否","综合交通","是","是","三岔河镇 ","投资已报完","投资已报完"]
[41,"凤庆县诗礼乡武伟村产业道路硬化项目","3月新建",2022,1250,0,900,1250,0,0,"否","否","综合交通","是","是","诗礼乡","投资已报完","投资已报完"]
[42,"凤庆县诗礼乡高标准农田建设项目","3月新建",2022,4000,0,4000,4000,0,0,"否","是","农业","是","是","诗礼乡","投资已报完","投资已报完"]
[43,"凤庆县诗礼乡人居环境提升项目","3月新建",2022,2100,0,1000,2100,0,0,"否","否","其他","是","是","诗礼乡","投资已报完","投资已报完"]
[44,"凤庆县诗礼乡30户以上自然村通硬化路建设项目","3月新建",2022,2000,0,2000,2000,0,0,"否","否","综合交通","是","是","诗礼乡","投资已报完","投资已报完"]
[45,"凤庆县诗礼乡孔兴村道路硬化项目","3月新建",2022,1200,0,1400,1200,0,0,"否","否","综合交通","是","是","诗礼乡","无","无"]
[46,"凤庆县大寺乡基层党群服务站建设项目","3月新建",2022,1012,0,1012,1012,0,0,"否","否","其他","是","是","大寺乡","投资已报完","投资已报完"]
[47,"凤庆县大寺乡美丽家园建设项目","3月新建",2022,2103,0,2103,2103,0,0,"否","否","其他","是","是","大寺乡","投资已报完","投资已报完"]
[48,"大寺乡环境综合整治建设项目","3月新建",2022,1675,0,1675,1675,0,0,"否","否","其他","是","是","大寺乡","投资已报完","投资已报完"]
[49,"凤庆县大寺乡德乐片区茶叶初制所建设项目","3月新建",2022,3420,0,3420,3420,0,0,"是","是","农业","是","是","大寺乡","投资已报完","投资已报完"]
[50,"凤庆县郭大寨乡西山片区旅游基础设施建设项目","3月新建",2022,1916,0,1916,1916,0,0,"否","否","文化旅游","是","是","郭大寨乡 ","投资已报完","投资已报完"]
[51,"凤庆县郭大寨乡邦贵村农产品初加工站基础设施建设项目","3月新建",2022,989,0,989,989,0,0,"是","是","农业","是","是","郭大寨乡 ","投资已报完","投资已报完"]
[52,"凤庆县郭大寨乡平掌村农产品初加工站基础设施建设项目","3月新建",2022,994,0,994,994,0,0,"是","是","农业","是","是","郭大寨乡 ","投资已报完","投资已报完"]
[53,"凤庆县郭大寨乡松林村阿腊山片区基础设施建设项目","2月新建",2022,1631,0,1631,1631,0,0,"否","否","其他","是","是","郭大寨乡 ","投资已报完","投资已报完"]
[54,"凤庆县新华乡紫微村等村组道路硬化建设项目","2月新建",2022,1200,0,1200,1200,0,0,"否","否","综合交通","是","是","新华乡 ","投资已报完","投资已报完"]
[55,"凤庆县新华乡美华村奴古彝寨乡村民族文化体验游开发项目","3月新建",2022,3906,0,3906,3906,0,0,"否","否","文化旅游","是","是","新华乡 ","投资已报完","投资已报完"]
[56,"腰街乡30户以上自然村通硬化路建设项目","2月新建",2022,3203.2,0,900,3203,0,0.199999999999818,"否","否","综合交通","是","是","腰街乡","投资已报完","投资已报完"]
[57,"凤庆县腰街彝族乡安平片区茶叶全产业链发展建设项目","3月新建",2022,2000,0,2000,2000,0,0,"是","是","能源以外工业","是","是","腰街乡","投资已报完","投资已报完"]
[58,"凤庆县腰街彝族乡水洗果加工站建设项目","3月新建",2022,1200,0,1200,1200,0,0,"是","是","能源以外工业","是","是","腰街乡","投资已报完","投资已报完"]
[59,"凤庆县腰街彝族乡民族文化广场建设综合项目","3月新建",2022,1500,0,1500,1500,0,0,"否","否","其他","是","是","腰街乡","投资已报完","投资已报完"]
[60,"凤庆县2022年核桃采后处理水洗果一级加工站建设项目","3月新建",2022,3000,0,3000,3000,706,706,"是","是","农业","是","是","县林草局","无","无"]
[61,"凤庆县红龟山绿化提升建设项目","3月新建",2022,732,0,732,732,0,0,"否","否","文化旅游","是","是","县林草局","投资已报完","投资已报完"]
[62,"凤庆县营林绿化建设项目","3月新建",2022,770,0,770,770,0,0,"否","是","农业","是","是","县林草局","投资已报完","投资已报完"]
[63,"凤庆县勐佑镇肖塘荷特色农耕文化休闲园建设项目","3月新建",2022,1460,0,1460,1460,0,0,"是","是","文化旅游","是","是","勐佑镇","投资已报完","投资已报完"]
[64,"凤庆县勐佑镇生物质燃料生产建设项目","3月新建",2022,1860,0,1860,1860,0,0,"是","是","能源","是","是","勐佑镇","投资已报完","投资已报完"]
[65,"凤庆县勐佑镇河西乡村旅游（一期）建设项目","3月新建",2022,1860,0,1860,1860,0,0,"否","是","文化旅游","是","是","勐佑镇","投资已报完","投资已报完"]
[66,"凤庆县勐佑镇村组道路硬化建设项目","3月新建",2022,1480,0,1480,1480,0,0,"否","否","综合交通","是","是","勐佑镇","投资已报完","投资已报完"]
[67,"凤庆县勐佑镇红色旅游基础设施建设项目","3月新建",2022,1420,0,1420,1420,0,0,"否","是","文化旅游","是","是","勐佑镇","投资已报完","投资已报完"]
[68,"凤庆县雪山镇桂林自然村整村推进项目","3月新建",2022,750,0,750,750,0,0,"否","否","其他","是","是","雪山镇","投资已报完","投资已报完"]
[69,"凤庆县雪山镇王家寨村游客接待服务中心建设项目","3月新建",2022,795,0,795,795,0,0,"否","否","文化旅游","是","是","雪山镇","投资已报完","投资已报完"]
[70,"凤庆县雪山镇东山片区农村污水处理项目","3月新建",2022,1125,0,1125,1125,0,0,"否","否","其他","是","是","雪山镇","投资已报完","投资已报完"]
[71,"凤庆县雪山镇生物质燃料厂建设项目","3月新建",2022,780,0,780,780,0,0,"是","是","能源","是","是","雪山镇","投资已报完","投资已报完"]
[72,"凤庆县雪山镇团圆养殖场建设项目","3月新建",2022,760,0,760,760,0,0,"是","是","农业","是","是","雪山镇","投资已报完","投资已报完"]
[73,"凤庆县彭家窝河田园综合体建设项目","4月新建",2022,2048,0,2048,2048,0,0,"是","是","文化旅游","是","是","县水务局","投资已报完","投资已报完"]
[74,"凤庆县2022年造林绿化建设项目","4月新建",2022,1800,0,1800,1800,0,0,"否","是","农业","是","是","县林草局","投资已报完","投资已报完"]
[75,"凤庆县油茶种植示范点建设项目","4月新建",2022,720,0,720,720,0,0,"否","是","农业","是","是","县林草局","投资已报完","投资已报完"]
[76,"凤庆县垃圾填埋场完善提升工程","4月新建",2022,1161,0,1161,1161,0,0,"否","否","其他","是","是","县住建局","无","无"]
[77,"勐佑镇义务教育薄弱环节改善与能力提升校舍建设项目","4月新建",2022,1000,0,1000,1000,0,0,"否","否","教育体育","是","是","县教体局","投资已报完","投资已报完"]
[78,"凤庆县营盘镇高标准农田地建设项目","4月新建",2022,1897,0,1897,1897,0,0,"否","是","农业","是","是","营盘镇","投资已报完","投资已报完"]
[79,"凤庆县营盘镇农业灌溉设施建设项目","4月新建",2022,3239,0,3239,3239,0,0,"否","是","农业","是","是","营盘镇","投资已报完","投资已报完"]
[80,"凤庆县雪山镇如美养殖场建设项目","4月新建",2022,663,0,663,663,0,0,"是","是","农业","是","是","雪山镇","投资已报完","投资已报完"]
[81,"凤庆县清凤帚加工厂建设项目","4月新建",2022,1000,0,1000,1000,0,0,"是","是","能源以外工业","是","是","凤山镇","投资已报完","投资已报完"]
[82,"凤山镇京竹林村二道河人饮工程项目","4月新建",2022,600,0,600,600,0,0,"否","否","水利","是","是","凤山镇","投资已报完","投资已报完"]
[83,"凤山镇平村大坟坝拆迁安置点基础设施建设项目","4月新建",2022,600,0,600,600,0,0,"否","否","其他","是","是","凤山镇","投资已报完","投资已报完"]
[84,"凤庆县老叶子茶叶加工厂建设项目","4月新建",2022,1600,0,1600,1600,0,0,"是","是","能源以外工业","是","是","凤山镇","投资已报完","投资已报完"]
[85,"凤庆县鲁史镇高标准农田建设项目","4月新建",2022,1800,0,1800,1800,0,0,"否","是","农业","是","是","鲁史镇","投资已报完","投资已报完"]
[86,"凤庆县鲁史镇永新片区人居环境综合提升建设项目","4月新建",2022,1440,0,1440,1440,0,0,"否","否","其他","是","是","鲁史镇","投资已报完","投资已报完"]
[87,"凤庆县鲁史镇茶旅融合发展建设项目","4月新建",2022,4600,0,4600,4600,0,0,"是","是","文化旅游","是","是","鲁史镇","投资已报完","投资已报完"]
[88,"凤庆县新华乡紫微村苗文化旅游开发项目","4月新建",2022,2154,0,2154,2154,0,0,"否","是","文化旅游","是","是","新华乡","投资已报完","投资已报完"]
[89,"凤庆县勐佑镇集镇基础设施建设项目","4月新建",2022,4620,0,4620,4620,0,0,"否","否","其他","是","是","勐佑镇","投资已报完","投资已报完"]
[90,"凤庆县三岔河镇生态农场建设项目","4月新建",2022,2630,0,2630,2630,0,0,"是","是","农业","是","是","三岔河镇","投资已报完","投资已报完"]
[91,"洛党镇大兴村育肥猪场建设项目","4月新建",2022,2780,0,2780,2740,0,40,"是","是","农业","是","是","洛党镇","无","无"]
[92,"凤庆县勐佑镇小尖山有机茶厂建设项目","5月新建",2022,3880,0,3880,3880,0,0,"是","是","能源以外工业","是","是","勐佑镇","投资已报完","投资已报完"]
[93,"勐佑镇休闲产业园建设项目","5月新建",2022,1230,0,1230,1230,0,0,"否","是","文化旅游","是","是","勐佑镇","投资已报完","投资已报完"]
[94,"凤庆县勐佑镇沪滇智慧农业示范园建设项目","5月新建",2022,500,0,500,500,0,0,"否","是","文化旅游","是","是","勐佑镇","投资已报完","投资已报完"]
[95,"凤庆县新华乡瓦屋片区人饮灌溉工程项目","5月新建",2022,1627,0,1627,1627,0,0,"否","否","水利","是","是","新华乡","投资已报完","投资已报完"]
[96,"凤庆县雪山镇农村人居环境提升建设项目","5月新建",2022,1531,0,1531,1531,0,0,"否","否","其他","是","是","雪山镇","投资已报完","投资已报完"]
[97,"凤庆县雪山镇土地坡改梯建设项目","5月新建",2022,2322,0,2322,2322,0,0,"否","是","农业","是","是","雪山镇","投资已报完","投资已报完"]
[98,"凤庆县三岔河镇棉花林村畜牧养殖场建设项目","5月新建",2022,650,0,650,650,0,0,"是","是","农业","是","是","三岔河镇","投资已报完","投资已报完"]
[99,"凤庆县三岔河镇大窝托片区基础设施建设项目","5月新建",2022,1890,0,1890,1890,0,0,"否","否","其他","是","是","三岔河镇","投资已报完","投资已报完"]
[100,"凤庆县云南一叶生物科技股份有限公司核桃蛋白粉生产线建设项目","5月新建",2022,2000,0,2000,2000,0,0,"是","是","能源以外工业","是","是","县工信局","投资已报完","投资已报完"]
[101,"凤庆县凤山镇安石村红茶产业2022年中央财政预算内以工代赈项目","5月新建",2022,1200,0,1200,1200,0,0,"否","否","其他","是","是","凤山镇","投资已报完","投资已报完"]
[102,"鲁史镇宝华片区田园综合体建设项目","5月新建",2022,1200,0,1200,1200,0,0,"是","是","文化旅游","是","是","鲁史镇","投资已报完","投资已报完"]
[103,"凤庆县郭大寨乡罗家寨村大树田片区基础设施建设项目","5月新建",2022,1429,0,1429,1429,0,0,"否","否","其他","是","是","郭大寨乡","投资已报完","投资已报完"]
[104,"凤庆县郭大寨乡平掌村大利茂片区基础设施建设项目","5月新建",2022,1230,0,1230,1230,0,0,"否","否","其他","是","是","郭大寨乡","投资已报完","投资已报完"]
[105,"云南省临沧市凤庆县通用机场场外排水影响区治理项目","5月新建","2022-2022",530,0,704,530,0,0,"否","否","其他","是","是","县水务局","资金未落实，工程未完工","投资已报完"]
[106,"凤庆县诗礼乡三合、牌坊片区道路基础设施建设项目","5月新建","2022-2023",4980,0,4980,4980,0,0,"否","否","综合交通","是","是","诗礼乡","投资已报完","投资已报完"]
[107,"临沧市凤庆县营盘镇秀塘村小坟山土地整治（提质改造）项目","5月新建","2022.02",2021,0,2021,2021,0,0,"否","是","农业","是","是","县自然资源局","投资已报完","投资已报完"]
[108,"凤山镇京竹林平掌自然村生态休闲游乐园建设项目","6月新建","2022-2022",700,0,700,700,0,0,"是","是","文化旅游","是","是","凤山镇","投资已报完","投资已报完"]
[109,"凤庆县2022年核桃采后处理水洗果二级加工站建设项目","6月新建","2022-2022",4760,0,4760,4760,0,0,"是","是","农业","是","是","县林草局","投资已报完","投资已报完"]
[110,"云南省临沧市凤庆县2022年高标准农田建设项目","6月新建","2022-2022",2230,0,2230,2230,0,0,"否","是","农业","是","是","县农业农村局","投资已报完","投资已报完"]
[111,"凤庆县黑河鲁史-新华段治理工程","6月新建","2022-2024",2421,0,600,612,0,1809,"否","否","水利","是","是","县水务局","下达的两条河道治理专项资金总额占比项目投资60%，需地方配套40%，且要求征地拆迁费用由地方自筹，相关设计、质量检测及监理服务费也尚未落实。","资金不到位（分年度下达资金），当年资金已完成，无法支撑今年投资"]
[112,"凤庆县2022年文庙片区打造历史文化街区建设项目","6月新建","2022-2022",1128,0,1457,1128,0,0,"否","否","其他","是","是","县住建局","无","无"]
[113,"凤庆县鲁史镇村组道路硬化建设项目","6月新建","2022-2022",1960,0,1960,1960,0,0,"否","否","综合交通","是","是","鲁史镇","投资已报完","投资已报完"]
[114,"鲁史镇永新片区茶叶初制所建设项目","6月新建","2022-2022",1320,0,1320,1320,0,0,"是","是","能源以外工业","是","是","鲁史镇","投资已报完","投资已报完"]
[115,"小湾镇锦秀村茶旅融合发展示范项目","6月新建","2022-2022",4200,0,4200,4200,0,0,"否","是","文化旅游","是","是","小湾镇","投资已报完","投资已报完"]
[116,"腰街彝族乡安平片区乡村振兴道路硬化建设项目","6月新建","2022-2022",797,0,797,797,0,0,"否","否","综合交通","是","是","腰街乡","投资已报完","投资已报完"]
[117,"凤庆县腰街彝族乡函关村茶厂建设项目","6月新建","2022-2022",1300,0,1300,1300,0,0,"是","是","能源以外工业","是","是","腰街乡","投资已报完","投资已报完"]
[118,"凤庆县腰街彝族乡星源村生猪养殖建设项目","6月新建","2022-2022",2000,0,2000,2000,0,0,"是","是","农业","是","是","腰街乡","投资已报完","投资已报完"]
[119,"凤庆县洛党镇露露农业综合休闲庄园建设项目","6月新建","2022-2022",3260,0,3260,3260,0,0,"是","是","文化旅游","是","是","洛党镇","投资已报完","投资已报完"]
[120,"凤庆县郭大寨乡大立色村坡坝片区基础设施建设项目","6月新建","2022-2023",1734,0,1734,1734,0,0,"否","否","其他","是","是","郭大寨乡","投资已报完","投资已报完"]
[121,"凤庆县智慧公园智慧系统平台建设项目","6月新建","2021-2022",8953,0,5000,8953,0,0,"否","是","数字经济","是","是","县住建局","无","无"]
[122,"凤庆县十八河河道治理（一期）建设项目","6月新建",2022,759,0,759,759,0,0,"否","否","其他","是","是","县住建局","投资已报完","投资已报完"]
[123,"凤庆县三岔河镇集镇功能提升建设项目","7月新建",2022,3085,0,3085,3085,0,0,"否","否","其他","是","是","三岔河镇 ","投资已报完","投资已报完"]
[124,"凤庆锦宏商务酒店建设项目","7月新建",2022,2000,null,2000,2000,0,0,"是","是","其他","是","是","凤山镇 ","投资已报完","投资已报完"]
[125,"凤庆中豪核桃加工厂建设项目","7月新建",2022,1800,null,1800,1800,0,0,"是","是","农业","是","是","凤山镇 ","投资已报完","投资已报完"]
[126,"凤庆县郭大寨乡松林村老尤寨片区烤烟产业基础设施建设项目","7月新建",2022,1216,null,1216,1216,0,0,"否","是","农业","是","是","郭大寨乡 ","投资已报完","投资已报完"]
[127,"凤庆县郭大寨乡邦贵村养殖场建设工程","7月新建",2022,1038,null,1038,1038,0,0,"是","是","农业","是","是","郭大寨乡 ","投资已报完","投资已报完"]
[128,"凤庆县诗礼乡2022年烤烟基础设施建设项目","7月新建",2022,800,null,800,800,0,0,"否","是","农业","是","是","诗礼乡","投资已报完","投资已报完"]
[129,"凤庆县营盘镇畜牧养殖建设项目","7月新建",2022,3592,null,3592,3592,0,0,"是","是","农业","是","是","营盘镇","投资已报完","投资已报完"]
[130,"凤庆县营盘镇乡村振兴兴农建设项目","7月新建",2022,3500,null,3500,3500,0,0,"否","是","农业","是","是","营盘镇","投资已报完","投资已报完"]
[131,"凤庆县营盘镇智慧生活购物商城","7月新建",2022,1300,null,1300,1300,0,0,"是","是","其他","是","是","营盘镇","投资已报完","投资已报完"]
[132,"凤庆县大寺乡大河片区茶旅融合建设项目","7月新建",2022,3100,null,3100,3100,0,0,"是","是","文化旅游","是","是","大寺乡","投资已报完","投资已报完"]
[133,"凤庆县雪山镇产业道路建设项目","7月新建",2022,1960,null,1960,1960,0,0,"否","否","综合交通","是","是","雪山镇","投资已报完","投资已报完"]
[134,"中电工程云南临沧三岔河镇100MW复核光伏发电项目","8月新建","2022-2023",45000,null,15000,2490,0,42510,"是","是","能源","是","是","县发改局","无建设指标","无建设指标"]
[135,"凤庆县干口农业光伏发电项目","8月新建","2022-2023",32524,null,20000,9994,4100,26630,"是","是","能源","是","是","县发改局","无","无"]
[136,"凤庆县洛党镇益民农业综合示范园建设项目（一期）","8月新建",2022,4632,null,4632,4632,0,0,"是","是","农业","是","是","洛党镇","无","无"]
[137,"凤庆县餐厨垃圾资源化处置项目","8月新建","2022-2023",4100,null,4100,1632,0,2468,"是","否","其他","是","是","县住建局","无","无"]
[138,"凤庆县标准化核桃加工厂建设项目","8月新建",2022,3980,null,3980,3943,0,37,"是","是","能源以外工业","是","是","县林草局","无","无"]
[139,"凤宁茶业加工厂二期建设项目","8月新建",2022,3718,null,3718,3718,0,0,"是","是","能源以外工业","是","是","县工信局","投资已报完","投资已报完"]
[140,"凤庆县新华乡砚田村民族团结进步示范村建设项目","8月新建",2022,1857,null,1857,1857,0,0,"否","是","农业","是","是","新华乡","投资已报完","投资已报完"]
[141,"凤庆县鲁史镇永新片区烤烟基础设施建设项目","8月新建",2022,1600,null,1600,1600,0,0,"是","是","农业","是","是","鲁史镇 ","投资已报完","投资已报完"]
[142,"凤庆县新华乡美华村农业综合示范区建设项目","8月新建",2022,559,null,559,559,0,0,"否","是","农业","是","是","新华乡","投资已报完","投资已报完"]
[143,"凤庆县诗礼中学学生宿舍食堂及运动场建设项目","8月新建","2022-2023",1152,null,1152,900,200,452,"否","否","教育体育","是","是","县教体局","无","无"]
[144,"万祥酒店综合楼建设项目","8月新建","2022-2023",1000,null,1000,1000,0,0,"是","是","其他","是","是","县工信局","投资已报完","投资已报完"]
[145,"凤庆县凤山镇滇红雅苑建设项目","9月新建","2022-2023",6000,null,3000,4367,371,2004,"是",null,"其他","是","是","县卫健局"]
[146,"凤庆鑫生源畜牧养殖场建设项目","9月新建",2022,2700,null,2700,2700,0,0,"是","是","农业","是","是","凤山镇","投资已报完","投资已报完"]
[147,"凤庆县腾源农产品初加工建设项目","9月新建",2022,2000,null,2000,2000,0,0,"是","是","能源以外工业","是","是","凤山镇","投资已报完","投资已报完"]
[148,"凤庆县雪山镇龚达茶叶加工厂建设项目","9月新建",2022,1786,null,1786,1786,0,0,"是","是","能源以外工业","是","是","雪山镇","投资已报完","投资已报完"]
[149,"凤庆县雪山镇建旭晟辉家禽养殖场建设项目","9月新建",2022,2480,null,2480,2482,0,-2,"是","是","农业","是","是","雪山镇","投资已报完","投资已报完"]
[150,"锦秀茶尊茶文化庄园建设项目","9月新建",2022,11257,null,9000,11257,1967,1967,"是","是","文化旅游","是","是","小湾镇"]
[151,"凤庆营盘现代农业综合体农产品加工区建设项目","9月新建",2022,6500,null,5000,6500,1035,1035,"是","是","能源以外工业","是","是","营盘镇"]
[152,"凤庆县大寺乡干塘山片区茶叶初制所建设项目","9月新建",2022,1160,null,1160,1160,0,0,"是","是","能源以外工业","是","是","大寺乡","投资已报完","投资已报完"]
[153,"新华乡紫微村平坦小组基础设施建设项目","9月新建",2022,845,null,845,845,0,0,"否","否","其他","是","是","新华乡 ","投资已报完","投资已报完"]
[154,"凤庆县营盘镇四个主体校园建设项目","9月新建",2022,2169,null,1000,2169,0,0,"否","否","教育体育","是","是","营盘镇"]
[155,"凤庆县营盘镇废旧机动车拆解回收利用项目","9月新建",2022,4786,null,4786,4786,0,0,"是","是","其他","是","是","县工信局"]
[156,"凤庆县勐佑镇畜牧业养殖厂建设项目","9月新建",2022,4125,null,4125,4125,0,0,"是","是","农业","是","是","勐佑镇"]
[157,"凤庆县洛党镇新城大沟防渗建设项目","9月新建",2022,3965,null,3965,3965,0,0,"是","是","其他","是","是","洛党镇"]
[158,"滇红凤锦建设项目（一期）","9月新建","2022-2023",25022,null,18000,11218,2463,16267,"是","否","房地产","是","是","县住建局"]
[159,"凤庆县三岔河镇松花村畜牧养殖场建设项目","10月新建",2022,2292,null,2292,2292,0,0,"是","是","农业","是","是","三岔河镇"]
[160,"凤庆县三岔河镇教育基础设施功能提升建设项目","10月新建",2022,1812,null,1812,1812,0,0,"否","否","教育体育","是","是","三岔河镇"]
[161,"凤庆县杨柳河肉牛养殖场BIPV屋顶分布式光伏发电项目","10月新建",2022,6450,null,6450,3511,0,2939,"是","是","能源","是","是","县农业农村局"]
[162,"云南省临沧市凤庆县2022年中央预算内投资高标准农田建设项目","10月新建",2022,4500,null,4500,4500,1968,1968,"否","是","农业","是","是","县农业农村局"]
[163,"凤庆县雪山镇教育基础设施提升建设改造项目","10月新建",2022,2232,null,2232,2232,0,0,"否","否","教育体育","是","是","雪山镇"]
[164,"凤庆县新华乡沙帽村漾江码头鱼产品仓储及初加工建设项目","10月新建",2022,1252,null,1252,1252,0,0,"否","是","能源以外工业","是","是","新华乡"]
[165,"凤庆陈昆养殖基地建设项目","10月新建","2022-2023",550,null,300,550,0,0,"是","是","农业","是","是","诗礼乡"]
[166,"凤庆县郭大寨乡郭大寨村鱼塘地片区基础设施建设项目","10月新建",2022,1807,null,1807,1807,0,0,"否","否","其他","是","是","郭大寨乡"]
[167,"凤庆县郭大寨乡平掌村青树片区基础设施建设项目","10月新建",2022,1947,null,1947,1947,0,0,"否","否","其他","是","是","郭大寨乡"]
[168,"东城完小义务教育薄弱环节改善与能力提升校舍建设项目","10月新建","2022-2023",600,null,400,400,100,300,"否","否","教育体育","是","是","县教体局"]
[169,"凤庆县2022年棚户区改造（白坟片区、窑上片区、小北门片区和双眼井片区）配套基础设施建设项目","10月新建","2022-2023",4723,null,3200,4723,1360,1360,"否","否","其他","是","是","县住建局"]
[170,"凤庆县鲁史镇团结片区农业基础设施建设项目","10月新建",2022,1860,null,1860,1860,0,0,"是","是","农业","是","是","鲁史镇"]
[171,"凤庆县腰街彝族乡高标准农田建设项目","10月新建",2022,1587,null,1587,1587,0,0,"否","是","农业","是","是","腰街乡"]
[172,"凤庆县腰街彝族乡无害化卫生厕所及污水收集处理建设项目","10月新建",2022,1219,null,1219,1219,0,0,"否","否","农业","是","是","腰街乡"]
[173,"凤庆县水磨河综合提升建设项目","10月新建","2022-2023",10200,null,2000,1810,813,9203,"是","否","其他","是","是","县住建局"]
[174,"临沧市凤庆县凤山镇安石村农村生活污水治理示范工程","10月新建",2022,500,null,500,500,0,0,"否","否","其他","是","是","凤山镇 "]
[175,"凤庆县2022年老旧小区改造（迎春小区三期等9个小区）配套基础设施建设项目","11月新建","2022-2023",3144,null,3144,3144,1442,1442,"否","否","其他","是","是","县住建局"]
[176,"勐佑镇易晨休闲园建设项目","11月新建","2022-2023",1960,null,1960,1960,480,480,"是","是","文化旅游","是","是","勐佑镇"]
[177,"勐佑镇界牌村春银茶叶初制所建设项目","11月新建","2022-2023",980,null,980,980,365,365,"是","是","农业","是","是","勐佑镇"]
[178,"凤庆县大寺乡路山村畜禽养殖场建设项目","11月新建","2022-2023",1685,null,1200,1685,470,470,"是","是","农业","是","是","大寺乡"]
[179,"凤庆县鲁史沧江沿岸乡村旅游建设项目","11月新建","2022-2023",1540,null,1540,1540,200,200,"是","是","文化旅游","是","是","鲁史镇"]
[180,"凤庆县雪山镇乡村旅游建设项目","11月新建","2022-2023",1596,null,1596,1596,446,446,"是","是","文化旅游","是","是","雪山镇"]
[181,"凤庆县雪山镇大山尖养殖场建设项目","11月新建","2022-2023",1828,null,1828,1828,428,428,"是","是","农业","是","是","雪山镇"]
[182,"凤庆县绿美集镇（雪山、洛党、小湾、勐佑等4个集镇示范点）建设项目","11月新建","2022-2023",3156,null,2000,2911,1029,1274,"否","否","其他","是","是","县住建局"]
[183,"凤庆县绿美城镇建设项目","11月新建","2022-2023",4876,null,2936,3660,1840,3056,"否","否","其他","是","是","县住建局"]
[184,"凤庆县陈氏农产品初加工建设项目","12月新建","2022-2023",1468,null,760,710,710,null,"是","是","农业","是","是","凤山镇"]
[185,"凤庆县新华乡沿江酒店及附属建设项目","12月新建","2022-2023",1440,null,1100,1100,1100,null,"是","是","文化旅游","是","是","新华乡"]
[186,"凤庆县鲁史镇新塘村马鹿塘组滑坡地质灾害治理项目","12月新建","2022-2023",1046,null,860,313,313,null,"是","是","其他","是","是","县自然资源局"]
[187,"凤庆县腰街彝族乡烤烟基础设施建设项目","12月新建","2022-2023",1389,null,1089,1289,1289,null,"是","是","农业","是","是","腰街乡"]
[188,"凤山镇麦地村丫口子、高峰片区乡村振兴基础设施建设项目","12月新建","2022-2023",750,null,384,365,365,null,"否","是","农业","是","是","凤山镇"]
[189,"凤庆县三岔河镇河东片区农业产业综合体建设项目","12月新建","2022-2023",1560,null,600,600,600,null,"是","是","农业","是","是","三岔河镇"]
[190,"凤庆县雪山镇王家寨村乡村旅游建设项目","12月新建","2022-2023",1889,null,1387,1387,1387,null,"否","是","文化旅游","是","是","雪山镇"]
[191,"凤庆县2022年农村公路提级工程","12月新建","2022-2023",655,null,360,454,454,null,"否","否","综合交通","是","是","县交运局"]
[192,"勐佑镇新林村德鹏茶叶初制所建设项目","12月新建","2022-2023",1825,null,1560,1560,1560,null,"是","是","农业","是","是","勐佑镇"]
[193,"小湾镇中草药种植项目","12月新建","2022-2023",4028,null,1502,1950,1950,null,"是","是","农业","是","是","小湾镇"]
[194,"凤山镇人居环境综合提升工程项目","12月新建","2022-2023",781,null,400,390,390,null,"是","是","其他","是","是","凤山镇"]
[195,"凤庆县雪山镇龚达养殖场建设项目","12月新建","2022-2023",1660,null,1300,1300,1300,null,"是","是","农业","是","是","雪山镇"]
[196,"凤庆县雪山镇源生茶叶加工厂建设项目","12月新建","2022-2023",1754,null,1360,1360,1360,null,"是","是","农业","是","是","雪山镇"]
[197,"小湾镇茶叶初制所规范化建设项目","12月新建","2022-2023",4745,null,1689,2290,2290,null,"是","是","农业","是","是","小湾镇"]
[198,"凤庆县勐佑镇有机茶所建设项目","12月新建","2022-2023",1986,null,1586,1586,1586,null,"是","是","农业","是","是","勐佑镇"]
[199,"凤庆县医疗设备采购项目","12月新建","2022-2023",622,null,622,622,622,null,"否","是","卫生健康","是","是","县卫健局"]
[200,"大寺乡路山村基础设施建设项目","12月新建","2022-2023",592,null,320,420,420,null,"否","是","综合交通","是","是","大寺乡"]
[201,"凤庆县乡村振兴”一县一业“核桃加工厂房建设项目","12月新建","2022-2023",19760.2,null,3000,3185,3185,null,"否","是","工业","是","是","园区管委会"]
[202,"凤庆县新华乡黑惠江文旅游客接待中心建设项目","12月新建","2022-2023",1370,null,1006,1006,1006,null,"是","是","文化旅游","是","是","新华乡"]
[203,"凤庆县智慧基础设施建设项目","12月新建","2022-2023",8000,null,1960,1961,1961,null,"否","否","其他","是","是","县住建局"]
[204,"凤庆县大寺乡淘金潭茶厂建设项目","12月新建","2022-2023",765,null,500,587,587,null,"是","是","农业","是","是","大寺乡"]
[205,"凤庆县郭大寨乡平掌村养殖场建设项目","12月新建","2022-2023",1327,null,600,601,601,null,"是","是","农业","是","是","郭大寨乡"]
[206,"凤庆县营盘镇乡村振兴农业产业建设项目","12月新建","2022-2023",10284,null,2500,2545,2545,null,"否","是","农业","是","是","营盘镇"]
[207,"黑惠江新华段垂钓基地及道路硬化建设项目","12月新建","2022-2023",1431,null,900,900,900,null,"是","是","文化旅游","是","是","新华乡"]
[208,"凤庆县腰街彝族乡晓美茶叶加工建设项目","12月新建","2022-2023",589,null,300,300,300,null,"是","是","农业","是","是","腰街乡"]
[209,"凤庆县诗礼乡清华村沿河自然村乡村振兴示范点建设项目","12月新建","2022-2023",800,null,600,650,650,null,"是","是","农业","是","是","诗礼乡"]
[210,"凤庆县大兴温泉核心区建设项目","12月新建","2022-2023",7700,null,6300,6211,6211,null,"是","是","文化旅游","是","是","县文旅局"]